## Slide 1: Project Cost Management
Notes: <number>

## Slide 2: Learning Objectives
Students understand the importance of project cost management
Students could explain :
  basic project cost management principles,
  concepts,
  terms
<number>

## Slide 3: What is Cost ?
something given up in exchange
are usually measured in monetary
<number>

## Slide 4: What is Project Cost Management?
processes required to ensure that the project is completed within an approved budget
<number>

## Slide 5: Processes:
Cost estimating:
estimate of the costs of the resources needed to complete a project
<number>

## Slide 6
Cost budgeting:
allocating the overall cost estimate to individual work items to establish a baseline for measuring performance
<number>

## Slide 7
Cost control:
controlling changes to the project budget
<number>

## Slide 8: Cost Estimating
Project managers should cost estimates seriously if they want to complete projects within budget constraints
<number>

## Slide 9: What components that u for estimating cost for your project?
Human resources
Previous work ( if you have).. As a template
Stake holder concept
Scope baseline ( wbs, milestone, project charter)
<number>

## Slide 10: Cost Estimation Tools and Techniques
Analogous or top-down estimates:
use the actual cost of a previous, similar project as the basis for estimating the cost of the current project
<number>

## Slide 11
Bottom-up estimates:
involve estimating individual work items or activities and summing them to get a project total
<number>

## Slide 12
Parametric modeling:
uses project characteristics (parameters) in a mathematical model to estimate project costs
<number>

## Slide 13
<number>

## Slide 14: Cost Budgeting
Cost budgeting involves allocating the project cost estimate to individual work items over time
The WBS is
  a required input to the cost budgeting process since it defines the work items
<number>

## Slide 15
<number>

## Slide 16
An important goal is to produce a cost baseline
Cost baseline :
  A time-phased budget that project managers use to measure and monitor cost performance
  created by estimating the costs by the particular period that the project would be completed.
  an important facet of the project management plan that companies use to ensure success
<number>

## Slide 17: Figure 7-4: Surveyor Pro Project Cost Baseline
<number>
*Numbers are rounded, so some totals appear to be off.

## Slide 18: Cost Control
Project cost control includes:
  Monitoring cost performance
  Ensuring that only appropriate project changes are included in a revised cost baseline
  Informing project stakeholders of authorized changes to the project that will affect costs
<number>

## Slide 19: Earned Value Management (EVM)
EVM is a project performance measurement technique that integrates scope, time, and cost data
Given a baseline (original plan plus approved changes), you can determine how well the project is meeting its goals
Note :
  You must enter actual information periodically to use EVM
<number>

## Slide 20
<number>

## Slide 21: Rules of Thumb for Earned Value Numbers
Problems occurs if :
SPI < 1  u behind the schedule
SV  sponsor benefit so the number should (+)
Your project over budget if :
  CPI<1
  CV ( -)
<number>

## Slide 22: To complete performance Index(TCPI)
TCPI jika dihitung dengan BAC untuk melihta apakah project anda masih bisa dijalankan atau tidak.
TCPI= (BAC-EV)/(BAC-AC)
 jika project anda sesuai dengan rencana
TCPI yang bernilai tinggi bearti budget anda sangat kecil.
<number>

## Slide 23
EAC ( estimation on completion)
EAC= BAC/CPI
TCPI= (BAC-EV)/(EAC-AC)
Untuk mengetahui bagaimana agar project anda tidak memiliki budget yang kecil.
<number>

## Slide 24: Cost Management Plan
A cost management plan
is a document that describes how the organization will manage cost variance on the project
<number>

## Slide 25: Contoh soal :
James dan Charles memiliki total budget sebesar Rp.10.000.000,- dan project yang mereka rencanakan sebesar 50%. Pekerjaan project mereka sebenarnya adalah 30%.
Hitunglah :
  BAC ( dalam Rp.)
  Rencana yang sudah berjalan ( dalam %)
  Biaya yang sudah berjalan (PV)
  Biaya yang sebenarnya (EV)
  Apakah anda sesuai dengan jadwal atau tidak? (SPI)
  Bagaimana keuntungan sponsor ?(SV)
<number>

## Slide 26: Jawab
BAC = 10 juta rupiah
Planned Complete = 50%
Actual complete = 30%
PV = BAC X50% = Rp. 5 Juta
EV= BAC X 30% = Rp. 3 Juta
SPI =EV/PV = 0.6
 project anda tertinggal jadwal yang anda perkirakan
SV = EV-PV = -Rp.2 juta
<number>

## Slide 27: Chapter Summary
Project cost management is
  A weakness area of IT projects,
  It is needed for a project managers to improve their ability to deliver projects within approved budgets
Main processes include:
  Cost estimating
  Cost budgeting
  Cost control
<number>

## Slide 28: Tugas kelompok :
Bagilah kelompok anda menjadi 2 buah kelompok.
Buatlah estimasi biaya untuk project software anda berdasarkan wbs yang telah anda buat. untuk project software yang sama
Berapa total budget untuk software anda?
Dikumpulkan tanggal 1 Desember 2011 paling lambat jam 12.00 wib di meja saya
<number>